## STATUS UPDATE
Overall Status Update for Project/Programme X
Main / Executive Commentary | [13 empty] | Overal RAG
Use this area for summary. Always begin with progression and positives then discuss key challenges and potential resolutions. Use actual names of people and do not create a culture of hiding from reporting RED/AMBER.
Key Exceptions
Project | Owner | RAG/Trend | Comment | [5 empty] | Path to green
Key Milestones/Project Progress
Milestone / Project Name | Owner | RAG / Trend | Completion Date | 2015-02-01 | 2015-03-01 | 2015-04-01 | 2015-05-01 | 2015-06-01 | 2015-07-01 | 2015-08-01 | 2015-09-01 | 2015-10-01 | 2015-11-01 | 2015-12-01 | 2016-01-01
Risks and Issues
Description |  |  | Owner | 2015-02-01: Risk/Issue; 2015-03-01: Date Raised; 2015-04-01: Mitigating actions (Resolution plan)
Key Exceptions [AUTOMATED FEED]
-This reads directly from the COMMENTARY tab
-Use this area to highlight the key concerns. By definition an Exception is something that has a RAG status of Amber or Red. It's less critical to discussion to focus on Greens since the due dilligence should have been done previously by the PMO to ensure all Greens are deserved
-There is only space for 3 entires, feel free to increase (insert rows and drag the formulas down) or decrease (delete rows). My tip is to not overwhelm the audience
Main / Executive Commentary [WRITE DIRECTLY IN HERE]
-This section is the overall commentary it should be drafted by the Project Manager if you are using this as a project update or by a Programme Manager/Executive if this is for a Programme/Portfolio level commentary
-Select an overall RAG status from the dropdown when you click in Cell K5
Key Milestones/Projects [AUTOMATED FEED]
-This reads directly from the MILESTONES tab.
-There is only space for 10 entries, feel free to increase (insert rows and drag the formulas down) or decrease (delete rows). My tip is to not overwhelm the audience
-Please note that for on screen viewing I have optimised the grid to display at 85% magnification (The Diamonds are 9point Arial Font). Printing is not affected. You will have to play around if you wish to adjust
DO NOT delete, clear or write over column A, it contains important formulas which help feed data in to the tables. I havecoloured the text white to hide it
DO NOT delete, clear or write over column L (L14 to L31) as it contains important formulas which help feed RAG data in to the Milestone table. I have coloured the text white to hide it
Key Risks and Issues [AUTOMATED FEED]
-This reads directly from the RISKS ISSUES tab
-There is only space for 5entries, feel free to increase (insert rows and drag the formulas down) or decrease (delete rows). My tip is to not overwhelm the audience

## RISKS ISSUES
Description | Owner | Risk/Issue | Date Raised | Mitigating actions (Resolution plan) | Include on front Page
This is a pretty serious Risk . It needs to be dealt with and escalated | Elliot Smith | Risk | 2015-01-13 | The only way to resolve this is to do exactly as stated in the following sentences
This is a pretty serious Issue . It needs to be dealt with and escalated | Kaki King | Issue | 2014-12-21 | The only way to resolve this is to do exactly as stated in the following sentences
This is a pretty serious Risk . It needs to be dealt with and escalated | Das Hoff | Risk | 2014-12-15 | The only way to resolve this is to do exactly as stated in the following sentences
This is a pretty serious Issue . It needs to be dealt with and escalated | Eva Cassidy | Issue | 2014-12-04 | The only way to resolve this is to do exactly as stated in the following sentences
This is a pretty serious Risk . It needs to be dealt with and escalated | Thom Yorke | Risk | 2014-11-21 | The only way to resolve this is to do exactly as stated in the following sentences
This is a pretty serious Risk . It needs to be dealt with and escalated | April Ludgate | Risk | 2014-11-15 | The only way to resolve this is to do exactly as stated in the following sentences
This is a pretty serious Risk . It needs to be dealt with and escalated | Tom Morello | Risk | 2014-10-13 | The only way to resolve this is to do exactly as stated in the following sentences
This is a pretty serious Issue . It needs to be dealt with and escalated | Alan Pacino | Issue | 2014-09-27 | The only way to resolve this is to do exactly as stated in the following sentences
This is a pretty serious Risk . It needs to be dealt with and escalated | Laura Marling | Risk | 2014-09-08 | The only way to resolve this is to do exactly as stated in the following sentences
This is a pretty serious Risk . It needs to be dealt with and escalated | Ann Perkins | Risk | 2014-08-09 | The only way to resolve this is to do exactly as stated in the following sentences
This is a pretty serious Risk . It needs to be dealt with and escalated | Amitabh Bachan | Risk | 2014-08-05 | The only way to resolve this is to do exactly as stated in the following sentences
Yes Count
0

## COMMENTARY
Milestone / Project Name | Owner | Current RAG | Previous RAG | Trend | Comment | Path to Green | Include on front Page
Release iPhone patch | Steve Jobs | R | R | n | It is absolutely essential to put commentary here as it is a Red RAG status so we need thorough explanation of what has happened | In all likelihood we will need to rebaseline or rescope the project/milestone in order to progress
Outline scheme for new build | Michael Bluth | A | A | n | Oh dear, Amber, we need an explanation of what has gone wrong. Ensure you don't stay in thos zone too long without reason. Many people view Amber as mismanaging | What are the salient moves that need to be executed to get us back on track ASAP?
Project Grace | Jeff Buckley | A | A | n | Oh dear, Amber, we need an explanation of what has gone wrong. Ensure you don't stay in thos zone too long without reason. Many people view Amber as mismanaging | What are the salient moves that need to be executed to get us back on track ASAP?
Source Mahogany for canoe | Ron Swanson | A | A | n | Oh dear, Amber, we need an explanation of what has gone wrong. Ensure you don't stay in thos zone too long without reason. Many people view Amber as mismanaging | What are the salient moves that need to be executed to get us back on track ASAP?
Create new alternative tuning | Nick Drake | G | A | h | Excellent, green is good, keep going, but you will be invovled in deep dives prior to delivery, consistent greens without much communication are not a good thing | No need, we are green!
Draft proposition to block Pawnchburger launch | Leslie Knope | G | G | n | Excellent, green is good, keep going, but you will be invovled in deep dives prior to delivery, consistent greens without much communication are not a good thing | No need, we are green!
Write score for Good Will Hunting 2: Hunting Season | Elliot Smith | A | A | n | Oh dear, Amber, we need an explanation of what has gone wrong. Ensure you don't stay in thos zone too long without reason. Many people view Amber as mismanaging | What are the salient moves that need to be executed to get us back on track ASAP?
Replace body of ovation to due pink noise | Kaki King | R | R | n | It is absolutely essential to put commentary here as it is a Red RAG status so we need thorough explanation of what has happened | In all likelihood we will need to rebaseline or rescope the project/milestone in order to progress
Renew Deutsch Passport | Das Hoff | G | R | h | Excellent, green is good, keep going, but you will be invovled in deep dives prior to delivery, consistent greens without much communication are not a good thing | No need, we are green!
Find something irreplaceable | Eva Cassidy | A | A | n | Oh dear, Amber, we need an explanation of what has gone wrong. Ensure you don't stay in thos zone too long without reason. Many people view Amber as mismanaging | What are the salient moves that need to be executed to get us back on track ASAP?
Project just cos you feel it, doesn't mean its there | Thom Yorke | A | G | i | Oh dear, Amber, we need an explanation of what has gone wrong. Ensure you don't stay in thos zone too long without reason. Many people view Amber as mismanaging | What are the salient moves that need to be executed to get us back on track ASAP?
Prepare for Vet school mid terms | April Ludgate | A | A | n | Oh dear, Amber, we need an explanation of what has gone wrong. Ensure you don't stay in thos zone too long without reason. Many people view Amber as mismanaging | What are the salient moves that need to be executed to get us back on track ASAP?
Replace whammy bar on strat | Tom Morello | B | G | h | Well done, the project/milestone is complete! | No need, we have completed!
Get cough medicine: hoo aaah | Alan Pacino | B | A | h | Well done, the project/milestone is complete! | No need, we have completed!
Return to incarnation as an Eagle | Laura Marling | A | A | n | Oh dear, Amber, we need an explanation of what has gone wrong. Ensure you don't stay in thos zone too long without reason. Many people view Amber as mismanaging | What are the salient moves that need to be executed to get us back on track ASAP?
Literally have a baby with Chris Trager | Ann Perkins | B | B | n | Well done, the project/milestone is complete! | No need, we have completed!
Purchase production house | Amitabh Bachan | R | R | n | It is absolutely essential to put commentary here as it is a Red RAG status so we need thorough explanation of what has happened | In all likelihood we will need to rebaseline or rescope the project/milestone in order to progress
Initiate project Comeback | Madhuri Dixit | A | R | h | Oh dear, Amber, we need an explanation of what has gone wrong. Ensure you don't stay in thos zone too long without reason. Many people view Amber as mismanaging | What are the salient moves that need to be executed to get us back on track ASAP?
Watch Red Dwarf to research hard light holograms | Tupac Shakur | A | R | h | Oh dear, Amber, we need an explanation of what has gone wrong. Ensure you don't stay in thos zone too long without reason. Many people view Amber as mismanaging | What are the salient moves that need to be executed to get us back on track ASAP?
Prada Hunter | Meryl Streep | G | A | h | Excellent, green is good, keep going, but you will be invovled in deep dives prior to delivery, consistent greens without much communication are not a good thing | No need, we are green!
Ensure entourage love it when they call me big Poppa | Notorious BIG | G | G | n | Excellent, green is good, keep going, but you will be invovled in deep dives prior to delivery, consistent greens without much communication are not a good thing | No need, we are green!
Hire someone to watch the throne | Jay Z | A | G | i | Oh dear, Amber, we need an explanation of what has gone wrong. Ensure you don't stay in thos zone too long without reason. Many people view Amber as mismanaging | What are the salient moves that need to be executed to get us back on track ASAP?
Deliver very strange time signature to Maynard | Danny Carey | B | B | n | Well done, the project/milestone is complete! | No need, we have completed!
Project timeline for next release spans 10000 days | Maynard James K | R | R | n | It is absolutely essential to put commentary here as it is a Red RAG status so we need thorough explanation of what has happened | In all likelihood we will need to rebaseline or rescope the project/milestone in order to progress
Yes Count
0

## MILESTONES
Timeline Range
|  | Start Date | 2015-02-01
|  | End Date | 2016-02-01
Milestone / Project Name | Owner | RAG/ Trend | Completion Date | 2015-02-01 | 2015-03-01 | 2015-04-01 | 2015-05-01 | 2015-06-01 | 2015-07-01 | 2015-08-01 | 2015-09-01 | 2015-10-01 | 2015-11-01 | 2015-12-01 | 2016-01-01 | Include on front Page | Feed from Commentary (for conditional formatting to work)
Release iPhone patch | Steve Jobs | n | 2016-01-03 | [13 empty] | R | bar: 2015-08-01; 2015-10-01; 2016-01-01
Outline scheme for new build | Michael Bluth | n | 2015-03-11 | [13 empty] | A | bar: 2015-03-01
Project Grace | Jeff Buckley | n | 2015-03-07 | [13 empty] | A | bar: 2015-03-01
Source Mahogany for canoe | Ron Swanson | n | 2015-03-15 | [13 empty] | A | bar: 2015-03-01
Create new alternative tuning | Nick Drake | h | 2015-05-27 | [13 empty] | G | bar: 2015-05-01
Draft proposition to block Pawnchburger launch | Leslie Knope | n | 2015-01-21 | [13 empty] | G
Write score for Good Will Hunting 2: Hunting Season | Elliot Smith | n | 2015-11-01 | [13 empty] | A | bar: 2015-06-01; 2015-08-01; 2015-10-01
Replace body of ovation to due pink noise | Kaki King | n | 2015-05-26 | [13 empty] | R | bar: 2015-05-01
Renew Deutsch Passport | Das Hoff | h | 2015-04-10 | [13 empty] | G | bar: 2015-04-01
Find something irreplaceable | Eva Cassidy | n | 2015-01-07 | [13 empty] | A
Project just cos you feel it, doesn't mean its there | Thom Yorke | i | 2015-03-23 | [13 empty] | A | bar: 2015-03-01
Prepare for Vet school mid terms | April Ludgate | n | 2015-02-08 | [13 empty] | A | bar: 2015-02-01
Replace whammy bar on strat | Tom Morello | h | 2015-02-06 | [13 empty] | B | bar: 2015-02-01
Get cough medicine: hoo aaah | Alan Pacino | h | 2015-06-13 | [13 empty] | B | bar: 2015-06-01
Return to incarnation as an Eagle | Laura Marling | n | 2015-04-15 | [13 empty] | A | bar: 2015-04-01
Literally have a baby with Chris Trager | Ann Perkins | n | 2015-01-05 | [13 empty] | B
Purchase production house | Amitabh Bachan | n | 2015-05-20 | [13 empty] | R | bar: 2015-05-01
Initiate project Comeback | Madhuri Dixit | h | 2015-03-01 | [13 empty] | A | bar: 2015-03-01
Watch Red Dwarf to research hard light holograms | Tupac Shakur | h | 2015-04-27 | [13 empty] | A | bar: 2015-04-01
Prada Hunter | Meryl Streep | h | 2015-04-27 | [13 empty] | G | bar: 2015-04-01
Ensure entourage love it when they call me big Poppa | Notorious BIG | n | 2015-04-26 | [13 empty] | G | bar: 2015-04-01
Hire someone to watch the throne | Jay Z | i | 2015-04-26 | [13 empty] | A | bar: 2015-04-01
Deliver very strange time signature to Maynard | Danny Carey | n | 2015-08-25 | [13 empty] | B | bar: 2015-06-01; 2015-08-01
Project timeline for next release spans 10000 days | Maynard James K | n | 2015-01-03 | [13 empty] | R
Yes Count
0

## How the Formulas work
I'm Sohail Anwar, the best way to get in touch with me is
Connect with me on LinkedIn
sohail.s.anwar@gmail.com
There is a video which accompanies this template so you can get a better understanding, it can be found at:
http://youtu.be/CyZ1LHzM5tU
This section will explain how the formulas in this template work
A few notes
Some of the formulas are advanced and look complicated, I urge you to persevere and read the guides/links to understand them. Get in touch if you are still struggling
For those familiar with 'Named Ranges', you will notice, I have not used them, this is because not everyone is familiar with Named Ranges, I didn't want to
create extra complexity and make it more difficult for people to learn/use the template. You can add them if you wish as it can improve the data management
Skip to section explaining
RISKS ISSUES Tab
COMMENTARY Tab
MILESTONES Tab
STATUS UPDATE Tab
RISKS ISSUES Tab
There are no important formulas here. In column F (highlighted Yellow) there is Data Validation to assign a "Yes" for a row you want to bring to the front page
There is a formula below the yellow highlighted are called 'Yes Count', this is a simple COUNTIF formula that helps you track how many "Yes's" you have checked
But it doesn't do anything of consequence
COMMENTARY Tab
There is some Data Validation and conditional formatting in Columns C & D, to assign the RAG status for each project/milestone
We also have the "Yes" column (H) as in the other tabs which will help us to feed information through to the STATUS UPDATE front page
Here is how the formula for 'Trend' in Column E works
This is a symbol to show if the status has improved (h), worsened (i) or remains the same (n) as last time
If you notice, the symbols are actually the characters 'h' , 'i' & 'n'. I have simply changed the font to WINGDINGS3
The formula compares the 'Current Status' with the 'Previous Status' which you need to populate
There are a number of ways to achieve the outcome to this formula, I will explain my logic and approach:
IF(MATCH(C2,{"R","A","G","B"},0)-MATCH(D2,{"R","A","G","B"},0)>0,"h",IF(MATCH(C2,{"R","A","G","B"},0)-MATCH(D2,{"R","A","G","B"},0)<0,"i","n"))
I have used a MATCH formula and defined my array as {R,A,G,B} the order is important, from worst (R) to best (B), The MATCH formula looks up the RAG status from column C
It will generate a number which is the position of the RAG in column C in the Array, so if C2 = "R" then the MATCH result in 1, a "A" would give 2, ""G" =3 and "B" = 4
So we have converted the RAG statuses in columns C and D in to numbers from 1 to 4. The IF formula subtracts those two numbers generated.
By subtracting those numbers, we either get:
A number greater than zero, in which case the IF will give us h
A number less than zero, in which case the IF will give us i
Otherwise it means the result is zero in which case the IF will give us n
MILESTONES Tab
Notice, how in column B,C and D I am just feeding the information from the COMMENTARY tab, this is to prevent duplication of static (not frequently changing) data
Ideally, we want to merge this tab with the COMMENTARY tab, but we have created a standalone report too
Here is an explanation of how the milestones grid and formula works:
Start of with the 'Start' and 'End' dates in E2,E3. These will set the range for the 6 month view, by driving the months in F5 to K5
You can only change the Start date, everything else will be based from that
Once you have that set, the formula depends largely on the value of the 'Completion date' in Column E
There are 6 formulas in each row, the all compare the completion date in Column E against the dates in the headers (F5 to K5)
For example if we are looking at the formula in row 7, then the IF formula in F7 is looking to see if the completion date (E7) is between F5 and G5
i.e. Is completion date E7 greater than the start of the current month or less than the start of the next month, each of the 6 formulas do this: IF(AND($E7+1>F$5,$E7<G$5)...
If this is true, i.e. if the completion date does lie between these two then the formula will plot the diamond symbol
The position of the diamond symbol is achieved through the use of the REPT formula (repeat), we simply repeat single spaces " " and add a "◆" on the end
If you look at the REPT formula, I have set the number of times to repeat the " " as $E7-F$5,this will give us number of days (between 0 and 30 at most)
I have optimsied the column width (11.43), the font /size (Arial 9 points) and the sheet magnification (85%) to allow 0 to 30 different positions, this is not exact but it's 99% accurate!
Finally, there is basic conditional formatting that affects the colour of the diamond symbol as in the screenshot below
We also have the "Yes" column (M) as in the other tabs which will help us to feed information through to the STATUS UPDATE front page
There is also a feed through of RAG statuses from the COMMENTARY tab in Column O to allow conditional formatting to be set in Column D
So Column D much more useful as we are conveying 2 bits of data in one cell (The current RAG status and whether it has improved) which is very efficient
STATUS UPDATE Tab
The status update consists of an area of merged cells towards the top where you can enter text as overall commentary, plus a RAG from the drop down
Then there are 3 sections: Commentary, Milestones and Risks/Issues, each of these sections are populated by feeding data from the other 3 corresponding tabs/sheets
I will explain the formulas in just one section as they are essentially the same, I will focus on the Milestones section
The most important set of formulas are hidden by colouring the text white, in column A, if you change the colour of the text to black, you can see them
The formulas here, look at the "Yes" column in the Milestones tab (Column M), the formula reads down that column
And whenever it finds a "Yes" (as set by you) then it will note the position (row) number of that Yes in the grid, so this formula just notes where the "Yes's" occur
It is an Array formula, it is quite tricky to explain here, but I have written an article on this particular formula that you can read here:
http://chandoo.org/wp/2014/12/09/multiple-occurrences-lookup-and-extraction/
Once we have the position numbers of the rows which have been marked "Yes" then, we use this information with a simple INDEX formula
As an example the formula in Cell B21 is: IFERROR(INDEX(MILESTONES!$A$6:$K$100,'STATUS UPDATE'!$A21,COLUMN()),""), let's break it down
So recalling that INDEX is a lookup formula which needs row/ column coordinates we are telling it to look in MILESTONES!$A$6:$K$100 grid (look up array)
Where the row 'co-ordinate' is A21 which is our Array formula that locates the row position of "Yes's"
The Column co-ordinate is the formula COLUMN(), what does this mean? =COLUMN() is a formula that result in the number of the column you write that formula in
For example if I write the formula =COLUMN() in cell F3, we get 6, because it just looks at the F and says, F is the 6th column...try it yourself!
So, why did I write this? It is because the sequence of columns in this section are matching the sequence of columns in the MILESTONE tab
So, by writing COLUMN() as the column position, we can easily drag our formula and save time not changing the column numbers in the INDEX formula!
Note: in other sections, sometimes there is a +1, -2 etc after the COLUMN(), just follow the formula to see why I have done that but it is usually
account for non sequential columns in the tabs where the information is fed from
Conditional Formatting of the grids
The conditional formatting of the colours is set by feeding through the values of the colours into Column L and hiding them by setting text to white
You can set the text to black to see the formulas, but again they are INDEX formulas just looking up the colour values
There is numerous kinds of conditional formatting going on here, there is a straightforward colour conditional formatting
One for the RAG status in column D, as you can see in the screenshot below, the we have simply set a formula to see what value is in L21 (B,R,A,G)
It affects the cell highlight, there is a similar conditional formatting which affects the grid, but this time it's the font colour which is affected
The final conditional formatting is a very important one as it creates a very useful illusion of a table, which automatically appears and disappears
The way I have achieved this is to use the setting which simply looks at the cell contents
If the cell is empty then there is no reason to have a table so it needs to look blank, this is done by saying Cell Value = "" then set the format to White color background
If the cell has something in it, it means we need to give it the illusion of automatically updating and increasing the table, so we write Cell Value <> ""
the <> means 'does not equal', then we set the formatting to 'No Color' background and a full table border (outline) around the cell
This conditional formatting really brings the template together as far the automatic feed throughs are concerned as you don't waste time formatting
If you have any questions about the template, you can get in touch at :
sohail.s.anwar@gmail.com